Step by Step Instructions

Planning a

Medical Scholars Academy

What to do before camp:

- Identify your collaborative partners

  - School districts (SUPERNet Consortia member districts)

  - Colleges

  - Hospitals

- Prepare a budget

- Identify your funding sources

  - Student fee (we keep ours at a maximum of $100 and we offer scholarships)

  - Partners

  - Vendors and/ or manufacturers

  - Grants and /or foundations

- Determine who will act as fiscal agent

- Determine who will provide transportation for the week

  - A local school district (a partner) provides a school bus

  - The district provides a driver who also serves as one of the counselors

- Determine who will act as counselors during the week

  - 3 adult volunteers (one of which is the bus driver)

  - 1 Junior counselor

- Determine date of the event

  - Registration is on Sunday afternoon

  - Banquet is on Thursday evening

  - Students depart after banquet

- Have all agreements, releases and forms approved by HR and/or legal dept.

- Reserve housing (I usually reserve six months in advance)

- Post application on web site and send announcements to partners (early spring)

- Set deadline to accept applications

  - Number the applications as they come in

  - The promptness of the application may help to break a tie when choosing participants

- Choose your participants

- Send out letter of acceptance along with packet of forms to be returned

- Send out letters of rejection (tell of other opportunities within your community)

- Determine who will be the guest speaker for the banquet

- Start working on schedule of events/activities

  - Training (HIPPA and Disease Prevention, CPR)

  - Setup job shadowing

  - Hospital Visits

  - Guest speakers

  - College and or University visits

  - Meals

  - Banquet

- Determine what you will offer for fun activities or break time

  - College Recreation Center

  - Movie night

  - Game night

- Order T-shirts

- Order Scrubs

- Prepare program for the banquet

- Put together welcome bag of goodies for the students

  - Toothbrush, toothpaste, small bar of soap, hand sanitizer, etc.

  - Promotional items from the colleges and hospitals

- Contact the news media

What to do during camp:

- Registration

  - Sunday afternoon

  - Ice Breaker Games

    - Scavenger hunt

    - Beach Ball game

  - HIPPA training

- Dinner

- Check in Dormitory

- Follow the detailed schedule of events for the camp

- Banquet to honor participants – Thursday evening

  - Invite parents,

  - Sponsors

  - Partners

  - and host site leaders

- Thank you notes to all partners, sponsors, and host sites

- Finalize your Expenses

Forms used and required

- Application

- Release of liability

  - From individual hospitals

  - Dormitory

  - Travel

  - Confidentiality

  - Student TB and Influenza attestation

  - Authorization for us of photograph, video or audiotape for promotional purpose

  - Emergency Contact/Medical Release

- Student dress code acknowledgement

- Packing list

Required for counselors

- Emergency Contact/Medical Release

- Child Protection Training